## Sheet1
Cape Elizabeth DEI Committee 2023 Plan Matrix (draft 11/28/22)
|  | 1 | 2 |  | 3 | 4 | 5
|  | CHALLENGE | VISION* FOR CAPE ELIZABETH | DEI LENS ON VISION STATEMENT | DEI COMMITTEE CHARGE^ | INTERIM OUTCOME | ACTIONS IN 2023 | METRICS/ MEASUREMENT
How the DEI Committee serves the town of Cape Elizabeth: | Areas of impact: | What issues must be addressed? | How does it tie to the town's Vision Statement? | How might a DEI lens be applied to the Vision Statement? | The Committee's Stated Charge is to: | What progress does the Committee want to make to address the challenge in the near term? | How will the Committee ensure progress? | How will the outcome be measured? (TBD based on iniatives prioritized)
We know our town | Knowledge of our community + willingness of residents to engage | Limited knowledge of town's needs and wants with respect to DEI | To encourage citizen engagement [the Committee will not succeed in engaging residents if it does not know what the town wants or needs] | We take an inclusive approach to data collection and planning for all members, and particularly marginalized members, of our community | (C) Elevate community engagement to better understand community views and concerns about diversity, equity, and inclusion | Generate increased data and knowledge about the citizens of Cape Elizabeth: who we are, who we want to be, and put a mechanism in place to remain connected to the pulse of our community | Conduct a survey of residents (e.g., polls, focus groups); invite Dear John/Love Letters; draft a Strategic Plan based on data | Response rate to survey (% of population); number of letter submissions; delivery of a Strategic Plan to the Town Council
We increase awareness [of benefits of DEI] to evolve thinking/ perspectives among members of our community | Attitudes + culture | Town has generally taken a reactive, rather than proactive, approach to DEI efforts; the root cause has not been identified or addressed |  | As a community, we can problem solve creatively and respectfully by incorporating myriad perspectives | (B) Educate the community to promote diversity, equity, and inclusion awareness and anti-racism | Execute one public, visible event and one town-focused education/policy initiative | Host a Human Library Project event in early fall 2023; deliver meaningful training to town personnel (It is Time); draft SMARTIE goals with each department/committee; establish a process to monintor/support the Cape Facebook POD | Positive first interaction with citizens, town employees, and committees (measured by exit surveys)
We address the root causes of discrimination to effect meaningful and enduring change | Systems | Systemic discrimination | To remain a highly desireable and welcoming community [the Committee can add value by reducing the barriers to joining, and thriving in, the community] | Equitiable access and opportunitity to become and remain a thriving community member/family | (A) Advise and recommend policies and practices to promote diversity, equity, and inclusion | Review and make recommendations on at least one of the town's core areas of operation using a DEI lens (e.g., policies, hiring practices, programs) | Make recommendations to edit, using a DEI lens, the DEI Committee's charge and the town's vision statement; DEI lense on public safety and Community Services; Housing policy and ballot wording | Recommendations are adopted, tracked, and reported on
*Taken from the Vision Statement in the Comprehensive Plan, 2019
^Taken from the Town Council's Charge for the DEI Committee, 2021